## Overview
SPRINT 1 PLANNING — TIMESHEET MANAGEMENT SYSTEM
Project: cnma-timesheet ¦ Sprint Duration: Feb 13 – Feb 20, 2026 ¦ Team Size: 3 Developers
SPRINT METADATA
| Sprint Number | Sprint 1
| Duration | 1 week (Feb 13 – Feb 20, 2026)
| Team Size | 3 Developers
| Target Launch | March 01, 2026
| Scrum Master | TBD
| Product Owner | TBD
SPRINT GOALS
| # | Goal Description | Category | Status | Owner | Priority
| 1 | Setup project structure and development environment | Foundation | Not Started | Tech Lead | HIGH
| 2 | Implement Authentication & User Management | Security | Not Started | TBD | HIGH
| 3 | Database design & setup for core entities (all 7 tables) | Data Layer | Not Started | TBD | HIGH
| 4 | Basic Timesheet entry UI (Manual logging) | Core Feature | Not Started | TBD | HIGH
KEY DELIVERABLES
| ✓ | React Frontend with basic routing & authentication
| ✓ | SAP CAP Backend with User, Project, Task, Timesheet, TimesheetEntry, ApprovalHistory, AuditLog entities
| ✓ | Database schema with proper relationships (7 tables, full FK coverage)
| ✓ | Login/Register UI complete
| ✓ | Timesheet entry form (manual input)
| ✓ | Project and Task selection dropdowns
| ✓ | Approval history tracking infrastructure
SUCCESS CRITERIA
| □ | User can login/logout successfully
| □ | User can create a new timesheet entry
| □ | System displays projects and tasks from the database
| □ | Database stores timesheet entries with proper validation
| □ | Approval history is tracked automatically on status changes
| □ | Code review completed for all features
| □ | Zero formula/data errors in the schema
ADDITIONAL SPRINT GOALS (from Role Analysis)
| # | Goal Description | Category | Status | Owner | Priority
| 5 | Approval workflow: DRAFT→SUBMITTED→APPROVED→REJECTED state machine | Workflow | Not Started | Full Stack Dev | HIGH
| 6 | Team Lead review dashboard (pending list, bulk approve/reject) | Core Feature | Not Started | Frontend Dev | HIGH
| 7 | aTrung Admin panel (edit approved entries, dashboard charts) | Core Feature | Not Started | Full Stack Dev | HIGH
| 8 | Excel export with pivot table (aTrung's template format) | Export | Not Started | Backend Dev | HIGH
| 9 | Email integration: send Excel to Germany (nodemailer/SMTP) | Integration | Not Started | Backend Dev | MEDIUM
| 10 | Notification system (submit/approve/reject triggers) | Core Feature | Not Started | Full Stack Dev | MEDIUM
| 11 | Papierkram API project sync (daily cron + manual trigger) | Integration | Not Started | Backend Dev | MEDIUM
| 12 | Audit log & export log tables + UI | Admin | Not Started | Backend Dev | MEDIUM
| 13 | Role-based access control (Staff / Team Lead / Admin guards) | Security | Not Started | Full Stack Dev | HIGH

## Database Design
SPRINT 1 — DATABASE DESIGN & SCHEMA
SAP CAP CDS Schema ¦ 7 Core Entities ¦ PostgreSQL / SAP HANA Compatible
ENTITY: User (cnma.timesheet.User)
| Field Name | Type | Required | Default | Description | Example | Notes
| id (cuid) | UUID/String(36) | Yes | Auto-generated | Primary key (CUID) | uu1d-xxxx-xxxx | @cuid from @sap/cds
| email | String(100) | Yes | — | Unique user email | alice@company.com | @mandatory, unique index
| firstName | String(50) | No | — | Given name | Alice | Display name
| lastName | String(50) | No | — | Family name | Smith | Display name
| role | UserRole enum | Yes | Employee | Employee / TeamLead / Manager / Admin | TeamLead | Controls access level
| isActive | Boolean | Yes | true | Soft-delete flag | true | Filter inactive users
| manager_id | Association→User | No | — | Self-ref to direct supervisor | uuid-of-teamlead | Hierarchy tree
| createdAt | DateTime | Yes | NOW() | Record creation time | 2026-02-13T08:00:00Z | Managed by @sap/cds
| modifiedAt | DateTime | Yes | NOW() | Last modification time | 2026-02-14T09:00:00Z | Auto-updated
ENTITY: Project (cnma.timesheet.Project)
| Field Name | Type | Required | Default | Description | Example | Notes
| id (cuid) | UUID/String(36) | Yes | Auto | Primary key | uu1d-proj-xxxx | @cuid
| name | String(100) | Yes | — | Project display name | Certificate Dev | @mandatory
| description | String(500) | No | — | Project description | Dev project for cert
| type | ProjectType enum | Yes | Others | Papierkram / Internal / External / Others | Papierkram | Drives billing rules
| code | String(20) | Yes | — | Short project code | CERT-2026 | @mandatory, display
| isActive | Boolean | Yes | true | Active flag | true | Hide archived
| user_id | Association→User | No | — | Project owner / manager | uuid-of-manager | Optional assignment
| createdAt | DateTime | Yes | NOW() | Created timestamp | 2026-02-13T08:00:00Z | Managed
| modifiedAt | DateTime | Yes | NOW() | Updated timestamp | 2026-02-14T09:00:00Z | Managed
ENTITY: Task (cnma.timesheet.Task)
| Field Name | Type | Required | Default | Description | Example | Notes
| id (cuid) | UUID/String(36) | Yes | Auto | Primary key | uu1d-task-xxxx | @cuid
| project_id | Association→Project | Yes | — | Parent project | uuid-of-project | @mandatory, FK
| name | String(100) | Yes | — | Task name | UI Design Sprint | @mandatory
| description | String(500) | No | — | Task details | Design login screen
| startDate | Date | No | — | Planned start date | 2026-02-13 | ISO 8601
| endDate | Date | No | — | Planned end date | 2026-02-20 | ISO 8601
| status | TaskStatus enum | Yes | Open | Open / InProgress / Completed / Cancelled | InProgress | Workflow state
| createdAt | DateTime | Yes | NOW() | Created timestamp | 2026-02-13T08:00:00Z | Managed
| modifiedAt | DateTime | Yes | NOW() | Updated timestamp | 2026-02-14T09:00:00Z | Managed
ENTITY: Timesheet (cnma.timesheet.Timesheet)
| Field Name | Type | Required | Default | Description | Example | Notes
| id (cuid) | UUID/String(36) | Yes | Auto | Primary key | uu1d-ts-xxxx | @cuid
| user_id | Association→User | Yes | — | Owner employee | uuid-of-user | @mandatory, FK
| month | Integer | Yes | — | Calendar month (1–12) | 2 | @mandatory
| year | Integer | Yes | — | Calendar year | 2026 | @mandatory
| status | TimesheetStatus | Yes | Draft | Draft/Submitted/Approved_By_TeamLead/Approved/Rejected/Finished | Submitted | Approval workflow
| submitDate | DateTime | No | — | When employee submitted | 2026-02-20T17:00:00Z | Nullable
| approveDate | DateTime | No | — | When fully approved | 2026-02-22T10:00:00Z | Nullable
| finishedDate | DateTime | No | — | When archived/finished | 2026-03-01T00:00:00Z | Nullable
| currentApprover_id | Association→User | No | — | Who must act next in workflow | uuid-of-teamlead | Nullable
| comment | String(1000) | No | — | Reviewer/employee comment | Please check hours
| createdAt | DateTime | Yes | NOW() | Created timestamp | 2026-02-13T08:00:00Z | Managed
| modifiedAt | DateTime | Yes | NOW() | Updated timestamp | 2026-02-14T09:00:00Z | Managed
ENTITY: TimesheetEntry (cnma.timesheet.TimesheetEntry)
| Field Name | Type | Required | Default | Description | Example | Notes
| id (cuid) | UUID/String(36) | Yes | Auto | Primary key | uu1d-entry-xxxx | @cuid
| timesheet_id | Association→Timesheet | Yes | — | Parent timesheet container | uuid-of-timesheet | @mandatory, FK
| project_id | Association→Project | Yes | — | Linked project | uuid-of-project | @mandatory, FK
| task_id | Association→Task | No | — | Optional task (finer granularity) | uuid-of-task | Nullable
| date | Date | Yes | — | Working date (not weekend) | 2026-02-13 | @mandatory, ISO 8601
| loggedHours | Decimal(5,2) | Yes | — | Hours entered by employee | 8.00 | Max 24, @mandatory
| approvedHours | Decimal(5,2) | No | — | Hours overridden by approver | 7.50 | Nullable
| hoursModifiedBy_id | Association→User | No | — | Who changed the approved hours | uuid-of-teamlead | Audit trail
| hoursModifiedAt | DateTime | No | — | When hours were changed | 2026-02-22T11:00:00Z | Audit trail
| description | String(500) | No | — | Task description / notes | [DEV] Login screen | User-entered
| createdAt | DateTime | Yes | NOW() | Created timestamp | 2026-02-13T08:00:00Z | Managed
| modifiedAt | DateTime | Yes | NOW() | Updated timestamp | 2026-02-14T09:00:00Z | Managed
ENTITY: ApprovalHistory (cnma.timesheet.ApprovalHistory)
| Field Name | Type | Required | Default | Description | Example | Notes
| id (cuid) | UUID/String(36) | Yes | Auto | Primary key | uu1d-ah-xxxx | @cuid
| timesheet_id | Association→Timesheet | Yes | — | Linked timesheet | uuid-of-timesheet | @mandatory, FK
| actor_id | Association→User | Yes | — | Who performed the action | uuid-of-teamlead | @mandatory
| action | String(30) | Yes | — | Submitted/Approved/Rejected/Modified/Finished | Approved | @mandatory
| fromStatus | TimesheetStatus | No | — | Previous workflow status | Submitted | For audit
| toStatus | TimesheetStatus | No | — | New workflow status | Approved_By_TeamLead | For audit
| comment | String(1000) | No | — | Reviewer comment | Looks good
| timestamp | DateTime | Yes | — | Exact action time | 2026-02-22T10:05:00Z | @mandatory, immutable
| createdAt | DateTime | Yes | NOW() | Record creation time | 2026-02-22T10:05:00Z | Managed
ENTITY: AuditLog (cnma.timesheet.AuditLog)
| Field Name | Type | Required | Default | Description | Example | Notes
| id (cuid) | UUID/String(36) | Yes | Auto | Primary key | uu1d-al-xxxx | @cuid
| entity_ | String(50) | Yes | — | Entity type name | TimesheetEntry | @mandatory
| entityId | String(36) | Yes | — | UUID of changed record | uu1d-entry-xxxx | @mandatory
| action | String(20) | Yes | — | Created / Updated / Deleted | Updated | @mandatory
| userId | String(36) | No | — | UUID of actor (denormalized) | uuid-of-user | Optional
| changes | String(2000) | No | — | JSON diff of changes | {"hours":"8→7.5"} | Compliance log
| createdAt | DateTime | Yes | NOW() | When log was written | 2026-02-22T10:05:00Z | Managed
ENUM TYPES & VALID VALUES
| Enum Name | Valid Values | Notes
| UserRole | Employee ¦ TeamLead ¦ Manager ¦ Admin | Controls UI visibility and API access permissions
| TimesheetStatus | Draft ¦ Submitted ¦ Approved_By_TeamLead ¦ Approved ¦ Rejected ¦ Finished | Approval workflow state machine
| TaskStatus | Open ¦ InProgress ¦ Completed ¦ Cancelled | Task lifecycle
| ProjectType | Papierkram ¦ Internal ¦ External ¦ Others | Drives billing, sync, and visibility rules
ENTITY RELATIONSHIPS & INDEXES
| From Entity |  | To Entity | Join Key | Description
| User (1) | → | Timesheet (N) | user_id FK | One user has many monthly timesheets
| Project (1) | → | Task (N) | project_id FK | One project has many tasks
| Project (1) | → | TimesheetEntry (N) | project_id FK | One project referenced in many entries
| Timesheet (1) | → | TimesheetEntry (N) | timesheet_id FK | One monthly sheet has many day entries
| Task (1) | → | TimesheetEntry (N) | task_id FK (nullable) | Optional task-level granularity
| Timesheet (1) | → | ApprovalHistory (N) | timesheet_id FK | Full audit trail per timesheet
| User (1) | → | ApprovalHistory (N) | actor_id FK | Who approved/rejected
RECOMMENDED INDEXES
| Entity | Index Columns | Type | Purpose
| User | email | Unique | Authentication lookup
| Project | code | Unique | Short-code lookup
| Task | project_id | Non-Unique | Filter tasks per project
| Timesheet | user_id, month, year | Unique | Prevent duplicate monthly sheets
| Timesheet | status | Non-Unique | Approval queue filtering
| TimesheetEntry | timesheet_id | Non-Unique | Fast entry listing
| TimesheetEntry | user_id, date | Non-Unique | Daily view queries
| ApprovalHistory | timesheet_id | Non-Unique | Audit trail lookup
| AuditLog | entity_, entityId | Non-Unique | Compliance trace

## Tech Setup
SPRINT 1 — TECHNICAL SETUP & ARCHITECTURE
Frontend: React + TypeScript ¦ Backend: SAP CAP (Node.js) ¦ DB: PostgreSQL / SAP HANA
FRONTEND STACK (React + TypeScript)
| Technology | Choice | Status | Owner | Notes
| Framework | React 18 + TypeScript | To Setup | Frontend Dev
| State Management | Zustand (lightweight) | To Setup | Frontend Dev | No Redux overhead
| Routing | React Router v6 | To Setup | Frontend Dev
| UI Library | Tailwind CSS + shadcn/ui | To Setup | Frontend Dev | Accessible components
| HTTP Client | Axios | To Setup | Frontend Dev | Interceptors for auth
| Form Handling | React Hook Form + Zod | To Setup | Frontend Dev | Schema validation
| Date Handling | date-fns | To Setup | Frontend Dev | Lightweight
| Build Tool | Vite | To Setup | Frontend Dev | Fast HMR
| Excel (client) | XLSX (SheetJS) | To Setup | Frontend Dev | Import parsing
BACKEND STACK (SAP CAP + Node.js)
| Technology | Choice | Status | Owner | Notes
| Framework | @sap/cds (CAP Framework) | To Setup | Backend Dev | OData V4 built-in
| Runtime | Node.js 18+ | To Setup | Backend Dev | LTS recommended
| Database | SQLite (dev) / SAP HANA (prod) | To Setup | Backend Dev | cds deploy --to sqlite
| Authentication | SAP BTP Auth / JWT | To Setup | Backend Dev | xs-security.json
| OData | OData V4 (built-in CAP) | To Setup | Backend Dev | Auto-generated
| API Docs | Swagger / OpenAPI | To Setup | Backend Dev | cds-swagger-ui
| Excel (server) | exceljs | To Setup | Backend Dev | Export generation
| Validation | CDS constraints + custom handlers | To Setup | Backend Dev | Entity-level rules
PROJECT DIRECTORY STRUCTURE
cnma-timesheet/
├── app/ # Frontend applications
│ └── timesheet-app/ # Main React application
│ ├── src/
│ │ ├── core/ # i18n, config
│ │ ├── features/ # admin, approvals, projects, timesheets
│ │ ├── shared/ # api, components, hooks, types
│ │ ├── App.tsx
│ │ └── main.tsx
│ └── package.json
├── srv/ # SAP CAP Backend service layer
│ ├── handlers/ # Custom TypeScript business logic
│ ├── admin-service.cds # Admin service definitions
│ ├── timesheet-service.cds # Main service definitions
│ └── package.json
├── db/ # Database layer
│ ├── data/ # Initial CSV seed data
│ └── schema.cds # CDS data models (7 entities)
├── docs/ # Project documentation
├── mta.yaml # SAP BTP deployment config
├── xs-security.json # Role & security config
└── README.md

## User Stories & Tasks
SPRINT 1 — USER STORIES & DEVELOPMENT TASKS
3 User Stories ¦ 25 Tasks ¦ Estimated ~60h ¦ Sprint: Feb 13–20, 2026
US-1: PROJECT SETUP & INITIALIZATION
| Story Points: 8 |  | Priority: HIGH |  | Owner: Tech Lead
| Task ID | Task Description | Type | Estimate | Owner | Status | Priority | Notes
| T-001 | Create project structure (monorepo) | Setup | 2h | TBD | To Do | HIGH | Frontend + Backend folders
| T-002 | Setup React 18 + TypeScript + Vite | Setup | 2h | TBD | To Do | HIGH | Use Vite template
| T-003 | Setup SAP CAP backend project (cds init) | Setup | 2h | TBD | To Do | HIGH | cds init cnma-timesheet
| T-004 | Configure Tailwind CSS + shadcn/ui | Setup | 2h | TBD | To Do | MEDIUM | Install base components
| T-005 | Setup SQLite (dev) / HANA connection (prod) | Setup | 1h | TBD | To Do | HIGH | cds deploy --to sqlite
| T-006 | Configure ESLint + Prettier | Setup | 1h | TBD | To Do | LOW | Code quality gates
| T-007 | Create README with setup guide | Docs | 1h | TBD | To Do | MEDIUM | For team onboarding
US-2: BASIC TIMESHEET ENTRY & DB SCHEMA
| Story Points: 13 |  | Priority: HIGH |  | Owner: Full Stack Dev
| Task ID | Task Description | Type | Estimate | Owner | Status | Priority | Notes
| T-201 | Define Projects entity in CDS schema | Backend | 2h | TBD | To Do | HIGH | Include all fields from schema.cds
| T-202 | Define Timesheets entity in CDS schema | Backend | 3h | TBD | To Do | HIGH | Monthly container entity
| T-203 | Define Task entity in CDS schema | Backend | 2h | TBD | To Do | HIGH | Link to Project, TaskStatus enum
| T-204 | Define TimesheetEntry entity in CDS schema | Backend | 2h | TBD | To Do | HIGH | loggedHours + approvedHours
| T-205 | Define ApprovalHistory entity in CDS schema | Backend | 2h | TBD | To Do | HIGH | Immutable audit trail
| T-206 | Define AuditLog entity in CDS schema | Backend | 1h | TBD | To Do | MEDIUM | Compliance / generic log
| T-207 | Create GET /projects endpoint | Backend | 2h | TBD | To Do | HIGH | List active projects
| T-208 | Create POST /timesheets endpoint | Backend | 3h | TBD | To Do | HIGH | Create monthly timesheet
| T-209 | Add validation rules (hours, date, required) | Backend | 2h | TBD | To Do | MEDIUM | Max 24h, no weekends
| T-210 | Create Timesheet Entry form UI | Frontend | 4h | TBD | To Do | HIGH | React Hook Form
| T-211 | Implement project + task dropdowns | Frontend | 2h | TBD | To Do | HIGH | Load from OData API
| T-212 | Add date picker (exclude weekends) | Frontend | 2h | TBD | To Do | MEDIUM | date-fns helpers
| T-213 | Create type selector (Papierkram/Internal/Others) | Frontend | 2h | TBD | To Do | MEDIUM | Radio buttons
| T-214 | Show success/error messages (toast) | Frontend | 1h | TBD | To Do | MEDIUM | Accessible notifications
US-3: EXCEL IMPORT / EXPORT
| Story Points: 13 |  | Priority: HIGH |  | Owner: Full Stack Dev
| Task ID | Task Description | Type | Estimate | Owner | Status | Priority | Notes
| T-301 | Install XLSX (SheetJS) library – frontend | Setup | 0.5h | TBD | To Do | HIGH | Client-side parsing
| T-302 | Install exceljs library – backend | Setup | 0.5h | TBD | To Do | HIGH | Server-side generation
| T-303 | Create Excel template parser (backend) | Backend | 3h | TBD | To Do | HIGH | Map columns to entity fields
| T-304 | Validate Excel data format & required cols | Backend | 2h | TBD | To Do | HIGH | Return row-level errors
| T-305 | Bulk insert TimesheetEntries from Excel | Backend | 3h | TBD | To Do | HIGH | Transaction + rollback
| T-306 | POST /timesheets/import endpoint | Backend | 2h | TBD | To Do | HIGH | Multipart file upload
| T-307 | GET /timesheets/export endpoint | Backend | 3h | TBD | To Do | HIGH | Generate formatted Excel
| T-308 | Build Import UI with drag & drop | Frontend | 3h | TBD | To Do | HIGH | File input + preview
| T-309 | Show import preview table (5-10 rows) | Frontend | 2h | TBD | To Do | MEDIUM | Before final confirm
| T-310 | Add Export button with Excel download | Frontend | 2h | TBD | To Do | HIGH | Trigger GET export
| T-311 | Handle import errors & display feedback | Frontend | 2h | TBD | To Do | MEDIUM | Show row + error message
| T-312 | Add template download link | Frontend | 1h | TBD | To Do | MEDIUM | Sample Excel file
SPRINT 1 SUMMARY
| Metric | Value
| Total User Stories | 3
| Total Story Points | 34
| Total Tasks | 33
| Estimated Hours | ~66h
| Team Velocity Target | 34 pts / 1 week
| Average Capacity / Dev | 22h (full capacity)

## Role & Workflow
SPRINT 1 — ROLE ANALYSIS & WORKFLOW DESIGN
3 Roles: Staff ¦ Team Lead ¦ aTrung (Admin) ¦ Source: Sprint1_Role_Analysis_EN.docx
ROLE OVERVIEW
| STAFF | Employee | Enters, edits, deletes, and submits own timesheet entries. Handles rejections and resubmissions.
| TEAM LEAD | Supervisor | Reviews pending timesheets from direct reports. Approves or rejects with comments. Views team reports.
| ADMIN (aTrung) | Administrator | Full system access. Edits approved timesheets, exports Excel to Germany, manages users & projects, views audit logs.
APPROVAL STATUS FLOW
| Status | Color Code | Actor | Description
| DRAFT | ● | Staff | Staff creates / edits entry
| SUBMITTED | ● | Staff | Staff submits to Team Lead
| APPROVED | ● | Team Lead | Team Lead approves
| Admin Export/Edit | ● | Admin | aTrung reviews, edits if needed, exports Excel
| REJECTED | ● | Team Lead | Team Lead rejects with reason → Staff edits & resubmits
ROLE 1: STAFF — Features & Technical Requirements
| Feature | Description | Technical Requirements
| Create Timesheet Entry | Enter: Date, Project, Type (Papierkram/Internal/Others), Task description, Hours, Working location, Note | React form + Zod validation. Date picker (exclude weekends). Project dropdown from API. Type selector (radio). Hours max 24h/day.
| Edit Timesheet | Edit entries with status = DRAFT only | GET /timesheets/:id → PUT /timesheets/:id. Guard: only allow edit when status = DRAFT.
| Delete Timesheet | Delete entries with status = DRAFT only | DELETE /timesheets/:id. Confirmation dialog. Guard: status = DRAFT only.
| View Timesheet List | Display own timesheets by day / week / month | GET /timesheets?user_id=current. Table with filters: date range, status. Pagination (100 items/page).
| Submit for Approval | Send DRAFT entries to Team Lead. Bulk submit supported (multiple entries at once). | POST /timesheets/submit Body: { timesheet_ids: [...] }. Status: DRAFT → SUBMITTED. Notification to Team Lead.
| View Approval Status | Check status badges: DRAFT / SUBMITTED / APPROVED / REJECTED | Color-coded badges: DRAFT=gray, SUBMITTED=yellow, APPROVED=green, REJECTED=red.
| Handle Rejection | View rejection reason from Team Lead, edit, and resubmit | Display rejection_note. Allow edit (status reset to DRAFT). Track submission history.
ROLE 2: TEAM LEAD — Features & Technical Requirements
| Feature | Description | Technical Requirements
| View Pending List | All timesheets with status = SUBMITTED from team members. Group by user & date. | GET /timesheets?status=SUBMITTED&team_id=current. Filters: user, date range, project. Highlight entries needing review.
| Review Entry Details | View full information per entry: user info, date, project, type, hours, task, location, note | GET /timesheets/:id. Modal / Detail view panel.
| Approve Timesheet | Approve one or multiple entries | POST /timesheets/approve Body: { timesheet_ids: [...] }. Status: SUBMITTED → APPROVED. Notify Staff & aTrung.
| Reject Timesheet | Reject with specific reason (rejection_note) | POST /timesheets/reject Body: { timesheet_ids: [...], rejection_note: '...' }. Status: SUBMITTED → REJECTED. Notify Staff.
| Bulk Approve / Reject | Select multiple entries via checkbox and approve or reject at once | Checkbox multi-select. Buttons: 'Approve Selected', 'Reject Selected'. Confirmation dialog before action.
| View Team Report | Summarize working hours by user, project, and period. Export to Excel. | Dashboard charts: Total hours by user, Hours by project, Weekly/Monthly trends. Export button.
| Approval History | Track all approved/rejected timesheets | GET /timesheets?status=APPROVED,REJECTED. Table: status, user, date range, approval_date, approved_by.
ROLE 3: aTRUNG (ADMIN) — Features & Technical Requirements
| Feature | Description | Technical Requirements
| View All Approved Timesheets | Full list of timesheets approved by Team Lead. Filters: user, team lead, date range, project, type, task description search. | GET /timesheets?status=APPROVED. Table view with full filter set.
| Overview Dashboard | Company-wide statistics: Total hours by team, Hours by project, Approved vs Pending ratio. Real-time updates. | Bar chart: Hours by team. Pie chart: Hours by project type. Line chart: Monthly trends.
| Edit Approved Timesheets | Edit approved entries if adjustments needed before export to Germany. Track original + edit history. | PUT /timesheets/:id (admin override). Editable: hours, task description, note. Log: edited_by, edited_at, original_value.
| Export Excel by Template | Export Excel per aTrung's format (with pivot table). Filter by: date range, team, project. | GET /timesheets/export?from=...&to=... . exceljs library. Columns: Date, User, Project, Type, Task, Hours, Location, Note. Pivot table: total hours by Project & User. Auto-width, borders, colors.
| Send Email to Germany | Attach Excel file and send to German team email with summary table. CC: Team Lead & aTrung. | nodemailer / SMTP integration. Email body: summary (total hours, breakdown by project). Attach exported Excel.
| Export History | Store all export history. Re-download previously exported files. | Table: export_logs. Fields: exported_by, export_date, from_date, to_date, total_entries, file_path.
| Manage Users | CRUD users, assign roles (Staff / Team Lead / Admin), assign Team Lead to Staff, deactivate/activate. | CRUD /users. Roles: STAFF, TEAM_LEAD, ADMIN. Soft-delete (isActive flag).
| Manage Projects | Sync projects from Papierkram API (daily cron + manual button). Activate/Deactivate projects. | Papierkram API integration. Cron job: daily sync. Manual sync button. POST /projects/sync.
| View Audit Logs | Who did what, when. Filter by user, action type, date range. | Table: audit_logs. Fields: user_id, action, entity_type, entity_id, timestamp, details.

## API & Feature Matrix
SPRINT 1 — API ENDPOINTS & FEATURE MATRIX
SAP CAP OData V4 ¦ RESTful endpoints ¦ Role-based access control
CORE API ENDPOINTS
| Method | Endpoint | Description | Staff | Team Lead | Admin
| POST | /timesheets | Create new timesheet entry | ✓ | — | —
| PUT | /timesheets/:id | Update timesheet (Staff=DRAFT only, Admin=any) | ✓ | — | ✓
| DELETE | /timesheets/:id | Delete timesheet (DRAFT only) | ✓ | — | —
| GET | /timesheets | List timesheets with filters (status, user, date range, project) | own | team | all
| GET | /timesheets/:id | Timesheet detail view | own | team | all
| POST | /timesheets/submit | Submit DRAFT entries to Team Lead (bulk supported) | ✓ | — | —
| POST | /timesheets/approve | Approve one or multiple SUBMITTED entries | — | ✓ | —
| POST | /timesheets/reject | Reject with rejection_note | — | ✓ | —
| GET | /timesheets/export | Export Excel (filter: from/to date, team, project) | — | — | ✓
| GET | /projects | List active projects | ✓ | ✓ | ✓
| POST | /projects/sync | Sync projects from Papierkram API (manual trigger) | — | — | ✓
| GET | /users | List users | — | team | ✓
| POST | /users | Create user | — | — | ✓
| PUT | /users/:id | Update user / assign role / deactivate | — | — | ✓
| GET | /audit-logs | View audit logs (filter: user, action, date) | — | — | ✓
| GET | /export-logs | View export history & re-download | — | — | ✓
FEATURE MATRIX BY ROLE
| Category | Feature | Staff | Team Lead | Admin
| Timesheet | Create entry (date, project, type, hours, location, note) | ✓ | — | —
|  | Edit entry (DRAFT only) | ✓ | — | —
|  | Delete entry (DRAFT only) | ✓ | — | —
|  | View own timesheets (day/week/month) | ✓ | ✓ | ✓
|  | Submit to Team Lead (bulk) | ✓ | — | —
|  | Handle rejection (edit & resubmit) | ✓ | — | —
| Approval | View pending (SUBMITTED) entries from team | — | ✓ | —
|  | Review entry details | — | ✓ | ✓
|  | Approve entry / bulk approve | — | ✓ | —
|  | Reject with reason / bulk reject | — | ✓ | —
|  | Edit approved entries (admin override) | — | — | ✓
| Reporting | View team working hours report | — | ✓ | ✓
|  | Dashboard charts (hours by team/project/month) | — | ✓ | ✓
|  | View approval history | — | ✓ | ✓
| Export | Export Excel by aTrung's pivot template | — | — | ✓
|  | Send Excel to Germany via email (nodemailer) | — | — | ✓
|  | View & re-download export history | — | — | ✓
| Admin | CRUD users & assign roles | — | — | ✓
|  | Sync projects from Papierkram API | — | — | ✓
|  | View audit logs | — | — | ✓
NOTIFICATION TRIGGERS
| Trigger Event | Notify | Message
| Staff submits timesheet | Team Lead | New submission pending review
| Team Lead approves | Staff + Admin | Timesheet approved
| Team Lead rejects | Staff | Timesheet rejected — see rejection_note
| Admin exports Excel | Admin (CC: TL) | Export completed — email sent to Germany
| Papierkram sync completes | Admin | Project list updated