## 1. Overview
TIMESHEET MANAGEMENT SYSTEM — REQUIREMENTS DOCUMENT
Project: cnma_timesheet ¦ Prepared by: Manh Cuong ¦ Date: Feb 07, 2026 ¦ Version: 01
PROJECT METADATA
| Project Name | cnma_timesheet
| Prepared By | Nguyen Manh Cuong
| Date | February 07, 2026
| Version | 01
| Target Launch | March 01, 2026
| Tech Stack | React / SAP CAP / SAP HANA / SAP BTP
PROJECT OBJECTIVES
| Main Goal | Replace the manual Excel-based timesheet process with an automated web application that allows staff to log time, team leads to approve, and aTrung (Admin) to export formatted Excel reports to the German team.
| Expected Benefits | Eliminate manual data consolidation; reduce errors in timesheet data; save 2–4 hours/week for aTrung; provide real-time visibility into team utilization and project hours.
| Success Metrics | 100% of staff submitting via system within 1 month of launch; export time reduced from hours to minutes; zero manual re-formatting needed for German report.
TOP PRIORITY QUESTIONS — MUST ANSWER BEFORE DEVELOPMENT
| Question | Answer / Status
| Number of users (Staff + Freelancer + Manager) | TBD — to be confirmed
| Launch timeline | March 01, 2026
| aTrung's current Excel export format | See 'Template' sheet for reference file
| Top 3–5 must-have features for launch | TBD — to be prioritised

## 2. Current Process
CURRENT PROCESS & PAIN POINTS
Documenting existing manual workflow to identify automation opportunities
CURRENT TIMESHEET LOGGING PROCESS
| Question | Answer / Details | Notes
| How many steps in the current process? | Excel → Papierkram → Send to aTrung → aTrung re-formats → Send to Germany | 5-step manual chain
| Who does each step and how long does it take? | Excel logging: Staff & Freelancers Log to Papierkram: Staff & Freelancers Send to aTrung: Staff & Freelancers Re-format/consolidate: aTrung Send to Germany: aTrung | aTrung's step is the bottleneck
| What columns does the current Excel template have? | See 'Template' sheet — Date, Type, Task, Working Location, Hours, Project (Papierkram), Note | Reference template attached
| What exactly does aTrung do when re-formatting? | Consolidates tasks from all team members by project, and adjusts hours to reasonable values | Manual, error-prone
| What filter criteria are used? | Primary focus: by project
| Who receives the final file and what is it used for? | The German team receives the final file for client-facing reporting and billing discussions | Critical output
PAIN POINTS & ISSUES
| Issue / Pain Point | Impact / Frequency | Priority (H/M/L)
How many hours per week/month are spent on manual timesheet logging?
What percentage of the work is manual and repetitive?
How many times per month are corrections or re-submissions needed due to errors?
What is the hardest or most error-prone step in the current process?
Which missing features cause the most difficulty?

## 3. User Roles
USER ROLES & PERMISSIONS MATRIX
Defines what each role can see and do within the system
ROLES DEFINITION
| Role | Description | Permissions Summary | Headcount
| Staff (Full-time) | Regular employee who logs their own daily timesheet entries | Log, edit (DRAFT), view own entries, submit for approval | TBD
| Team Lead | Supervisor who reviews and approves timesheets for their direct reports | All Staff permissions + view team entries, approve/reject, view team reports | TBD
| aTrung (Admin) | System administrator; consolidates approved timesheets and exports to Germany | Full access: edit approved entries, export Excel, send email, manage users & projects | 1
PERMISSIONS MATRIX
| Feature / Action | Staff | Team Lead | aTrung (Admin)
| Log own timesheet | ✓ | ✓ | ✓
| View own timesheet | ✓ | ✓ | ✓
| Edit own timesheet (before approval) | ✓ | ✓ | ✓
| Edit own timesheet (after approval) | ✗ | ✗ | ✓ (override)
| View team members' timesheets | ✗ | ✓ (own team) | ✓ (all)
| Approve timesheets | ✗ | ✓ | ✓
| Reject timesheets | ✗ | ✓ | ✓
| Bulk approve / reject | ✗ | ✓ | ✓
| Export reports to Excel | ✗ | partial | ✓
| Send email to Germany | ✗ | ✗ | ✓
| Manage projects (sync Papierkram) | ✗ | ✗ | ✓
| Manage users & assign roles | ✗ | ✗ | ✓
| View audit logs | ✗ | ✗ | ✓

## 4. Timesheet Logging
TIMESHEET LOGGING — FUNCTIONAL REQUIREMENTS
Covers quick logging, task tracking, and validation rules
1. QUICK TIMESHEET LOGGING
| Question | Answer / Details | Priority (H/M/L)
| Minimum required fields when logging? | Date, Project, Type (Papierkram / Internal / Others), Task description, Hours, Working Location, Note | H
| Log regular hours vs overtime separately? | No — logging more than 8h/day automatically counts as OT; OT is calculated separately on the OT side | H
| Log by individual activity or total hours per day? | Log by individual activity (multiple entries per day are allowed) | H
| Allow logging future dates? (Plan ahead) | Yes — future date logging is permitted | M
| Allow logging past dates? Any limit? | Yes — no restriction on past dates at this stage | M
2. TASK TRACKING
| Question | Answer / Details | Priority (H/M/L)
| What is a 'task'? (project-based, activity-based, ticket-based?) | A task can be a project, an activity, or a ticket — flexible definition | M
| Who creates tasks? (Manager, staff self-create, import from Jira?) | Tasks are created by staff themselves when logging time | M
| Is task status tracking needed? (Todo / In Progress / Done) | No — task status tracking is not required | L
| Is Estimate hours vs Actual hours tracking needed? | No — not required | L
| Is task hierarchy needed? (Project > Task > Subtask) | No — flat task structure only | L
| Does a task need to be assigned to a specific person? | No — assignment is not required | L
| Do tasks have deadlines? | No — deadlines are not required | L
3. VALIDATION RULES
| Rule | Detail / Logic | Required?
| Maximum hours per day? | e.g. No more than 16h/day | TBD
| Minimum hours per day? | e.g. At least 1h if a log exists | TBD
| Overtime rules? | >8h/day? >40h/week? >176h/month? | TBD
| Warning if too many hours logged? | Show alert but do not block | TBD
| Block submit if required fields missing? | Block form submission until fields filled | TBD
| Allow logging 0 hours? | TBD | TBD

## 5. Approval Workflow
APPROVAL WORKFLOW — REQUIREMENTS
Defines the review, approve, reject flow from Staff → Team Lead → Admin
1. APPROVAL PROCESS Q&A
| Question | Answer / Details | Notes
When is approval required? (Daily / Weekly / Bi-weekly / Monthly?)
Who approves? (Direct manager, PM, aTrung?)
Is multi-level approval needed? (Level 1: Manager, Level 2: Finance?)
Approve entire timesheet or individual entries?
Approve by period or by individual day?
On rejection: does staff edit and re-submit, or does it auto-revert to draft?
Is there a submission deadline? (e.g. 3 days after the week ends?)
Is there a penalty for late submission?
Can manager edit directly or only approve / reject?
Are notifications sent when a timesheet is pending approval?
2. APPROVAL STATUS & WORKFLOW
| Status | Meaning / Available Actions | Next Status
| Draft | Staff is creating or editing the entry. Can be edited or deleted freely. | Submitted
| Submitted | Staff has submitted for review. Locked from editing. Awaiting Team Lead action. | Approved / Rejected
| Approved | Team Lead has approved. aTrung can view, optionally edit, and export. | Locked / Finished
| Rejected | Team Lead has rejected with a reason. Staff must edit and re-submit. | Draft (re-submit)
| Locked (Final) | Export completed. Entry is fully finalised and archived. | —

## 6. Export & Integration
EXPORT & INTEGRATION — REQUIREMENTS
Excel export for Germany, Papierkram API sync, and other integrations
1. EXCEL EXPORT
| Question | Answer / Details | Sample / Reference
| What columns does aTrung's Excel template require? | See 'Template' sheet — Date, Type, Task, Working Location, Hours, Project (Papierkram), Note | Template sheet
| How many export formats are needed? | TBD — at minimum: one format for the German team
| Export period? (Daily / Weekly / Monthly / Custom range?) | TBD
| Export per person or for the whole team? | TBD — likely per person for Germany, whole team for internal use
| Export by project or by team? | TBD — primary focus: by project
| Does the export need a summary row/sheet? (Total hours, OT hours?) | TBD
| Does the export need pivot / group-by? (By project, by person, by type?) | TBD — pivot table required per aTrung's current template
| File naming convention? | 2025_12_Timesheet_Nguyen_Manh_Cuong.xlsx | Confirmed
2. PAPIERKRAM INTEGRATION
| Question | Answer / Details | Documentation
| Does Papierkram have API documentation? | Yes — https://api-doc.papierkram.de/api/v1/api-docs/index.html | Link confirmed
| API type? | REST API
| Authentication method? | API Token (HTTP Bearer token) | Confirmed
| Sync mode: real-time or batch (scheduled)? | TBD
| When to sync? (After save, after approve, on schedule?) | TBD
| Data mapping: System fields → Papierkram fields? | TBD — mapping document needed
| If sync fails: retry, alert, or manual fallback? | TBD
| Is 2-way sync needed? (Papierkram → new system?) | TBD
| API rate limit? (Requests per minute?) | TBD — check Papierkram docs
3. OTHER INTEGRATIONS
| Integration | Required? (Y/N/Maybe) | Purpose / Details
| Email notification (Gmail / Outlook) | TBD | Notify on submit / approve / reject
| Slack notification | TBD
| Microsoft Teams | TBD
| Google Calendar (auto-block time) | TBD
| Jira (import tasks) | TBD
| MISA (accounting system) | Y | Integration confirmed as needed
| SAP (if applicable) | TBD
| Bulk import from Excel | Y | Staff should be able to import from Excel template

## 7. Reports & Analytics
REPORTS & ANALYTICS — REQUIREMENTS
Required reports, dashboard specs, and filter requirements
1. REQUIRED REPORTS
| Report Name | Details / Metrics | Priority (H/M/L)
| Overtime Report | How much OT did the team log this month? — Total OT hours per person, OT by project, OT trend | H
| Productivity Report | Hours logged vs expected hours; actual vs estimate | M
| Project Utilization Report | Hours by project, project progress, budget tracking | H
| Billable vs Non-Billable | Revenue hours (Papierkram projects) vs internal hours | H
| Cost Report | Total cost by project (if rate data is available) | M
| Compliance Report | Who has not yet submitted their timesheet? Late submission tracking | H
| Team Capacity Report | Total available hours, hours used, remaining capacity | M
| Individual Summary | My hours this month, my OT hours, my projects breakdown | H
2. DASHBOARD REQUIREMENTS
| Question | Answer / Details | Notes
What KPIs / charts / summaries should the dashboard show?
Real-time data or end-of-day data?
Period comparison needed? (This month vs last month?)
Drill-down needed? (Click a number to see detail?)
Which roles have a dashboard? (Manager, Admin, Staff?)
Status widgets needed? (Pending approvals, late submissions?)
Chart types needed? (Bar, Line, Pie, Table?)
Export dashboard to PDF / Excel?
3. FILTERS & DATE RANGES
| Filter Type | Options / Details | Required?
| Date Range | Today / This Week / This Month / Last Month / Custom range
| By Person | Single person / Multiple / All team
| By Project | Single project / Multiple / All projects
| By Status | Draft / Submitted / Approved / Rejected
| By Type | Papierkram / Internal / Others
| By Client | If applicable

## 8. Technical
TECHNICAL REQUIREMENTS
Security, performance, and confirmed technology stack
1. ACCESS & SECURITY
| Question | Answer / Details | Notes
Who can view whose timesheet? (Own only / Team / All company?)
Is an audit trail needed? (Who edited what and when?)
Is edit restricted after approval?
Is there a lock period? (e.g. Cannot edit timesheet older than 30 days?)
Is mobile access required? (Responsive web or native app?)
| Authentication method? | SAP BTP OAuth (confirmed) | ✓ Confirmed
2. PERFORMANCE & SCALABILITY
| Question | Answer / Details | Notes
How many concurrent users? (Peak load?)
Data retention period? (1 year / 3 years / 5 years?)
Expected data volume? (Records per month / year?)
Response time expectations? (<1s / <3s / <5s?)
Are bulk operations needed? (Import 1,000+ entries?)
Is offline mode required? (Work without internet?)
Backup frequency? (Daily / Weekly?)
Disaster recovery plan required?
3. CONFIRMED TECHNOLOGY STACK
| Component | Technology / Preference | Notes
| Frontend | React.js + Next.js + TypeScript | ✓ Confirmed
| Backend | SAP CAP + Node.js + TypeScript | ✓ Confirmed
| Database | SAP HANA | ✓ Confirmed
| Cloud Platform | SAP BTP + Azure | ✓ Confirmed
| Hosting | Cloud Foundry | ✓ Confirmed
| CI/CD | Jenkins + Azure DevOps | ✓ Confirmed
| Authentication | SAP BTP OAuth | ✓ Confirmed
| Excel Export | exceljs (server-side) | Recommended
| Excel Import | SheetJS / XLSX (client-side) | Recommended

## 9. Nice-to-Have
NICE-TO-HAVE FEATURES — FUTURE ENHANCEMENTS
Post-launch wishlist — not required for Sprint 1 MVP
FUTURE FEATURES WISHLIST
| Feature | Description / Use Case | Interest Level (H/M/L)
| Copy Timesheet | Copy entries from a previous day/week, or use templates for recurring tasks | H
| Auto-suggestion | Suggest projects and tasks based on the user's history | H
| Calendar View | Visual calendar to log time via drag-and-drop | M
| Team Calendar | View the whole team's activities and availability | M
| Native Mobile App | iOS / Android native app (beyond responsive web) | M
| Offline Mode | Log timesheet offline and sync when internet is available | M
| Calendar Integration | Sync with Google / Outlook calendar; auto-create timesheet entries from events | M
| Time Tracking Widget | Start / Stop timer for real-time tracking | M
| Screenshot / Proof | Attach screenshot or proof of work to an entry | L
| AI Suggestions | AI-generated task descriptions and auto-categorisation | M
| Voice Input | Log timesheet entries using voice commands | L
| Gamification | Badges and achievements for timely submission | L
| Analytics Insights | AI insights: 'You worked 20% more OT than last month' | M
| Resource Forecasting | Predict future team capacity based on historical data | M
| Invoice Generation | Auto-generate invoices from billable hours | H

## 10. Success Criteria
SUCCESS CRITERIA & KPIs
Measurable targets to evaluate whether the system is achieving its goals
1. TIME SAVINGS
| Metric | Current State | Target State
| Time to log timesheet per week (per person) | TBD | < 15 min/week
| Time to process / export timesheet per week (aTrung) | TBD | < 30 min/month
| Time to sync with Papierkram per week | TBD | Automated / 0 min
| Time to generate reports per month | TBD | < 5 min
| Number of manual steps in the process | 5 steps | ≤ 2 steps
2. ACCURACY & COMPLIANCE
| Metric | Current State | Target State
| Error rate in timesheet data | TBD | < 2%
| % of timesheets submitted on time | TBD | > 95%
| % of timesheets approved on first submission (no rejection) | TBD | > 90%
| % of manual work vs automated | TBD | < 10% manual
3. USER ADOPTION
| Question / Metric | Target | How to Measure
| Time for staff to become familiar with the system | < 1 week | Training sessions + support tickets
| User satisfaction score target | ≥ 4 / 5 | Monthly survey
| % of users actively using the system after 3 months | > 95% | Login analytics
| Number of support tickets / issues per month | < 5 / month | Helpdesk tracking
| User feedback score after 1 month | ≥ 4 / 5 | In-app survey
4. ROI & BUSINESS VALUE
| Question | Answer / Calculation | Notes
| Cost savings per month? | Hours saved × hourly rate | TBD once hours measured
| Break-even point? | Development cost ÷ monthly savings | TBD
| Productivity improvement? | % increase in billable hours | TBD
| Quality improvement? | % reduction in data errors | TBD
| Business value beyond time savings? | Better visibility, compliance, audit trail | Qualitative

## 11. Rate & Cost
RATE & COST MANAGEMENT — REQUIREMENTS
Staff rates, OT multipliers, freelancer rates, and cost reporting
1. RATE STRUCTURE Q&A
| Question | Answer / Details | Notes
Different rates for Staff vs Freelancers?
Rate basis? (Hourly / Daily / Monthly?)
Rate varies by seniority? (Junior / Mid / Senior?)
Rate varies by work type? (Dev / Testing / Support?)
Rate varies by project / client?
Minimum billable unit? (15 min / 30 min / 1 hour?)
Rounding rule? (e.g. 1.2h → 1.5h?)
Do rates have an expiry date? (Effective from – to?)
2. STAFF RATE TABLE (Reference / Example)
| Rate Type | Details / Rules | Example Rate
| Standard Rate | Regular hours within standard working hours | 500,000 VND / hour
| OT Rate — Weekday | Overtime on a normal working day (> 8h/day) | 750,000 VND / hour (1.5×)
| OT Rate — Weekend | Overtime on Saturday or Sunday | 1,000,000 VND / hour (2×)
| OT Rate — Public Holiday | Overtime on an official public holiday | 1,500,000 VND / hour (3×)
| Night Shift Rate | Night shift work (if applicable) | 600,000 VND / hour (1.2×)
| Internal Rate | Rate applied to internal / non-billable projects | 400,000 VND / hour
| Cost Rate | Internal cost rate for project profitability calculation | 300,000 VND / hour
3. COST REPORTS NEEDED
| Report Type | Calculation Method | Required? (Y/N)
| Project Cost Report | Total hours × rate by project
| Person Cost Report | Total cost per person per period
| Billable Revenue Report | Billable hours × rate
| Cost vs Revenue | Compare cost rate vs billable rate
| Utilization Rate | Billable hours ÷ total available hours
| Profitability by Project | Revenue − Cost by project
| Budget vs Actual | Project budget vs actual cost incurred

## 12. OT Management
OVERTIME (OT) MANAGEMENT — REQUIREMENTS
OT rules, multipliers, auto-detection, approval workflow, and reporting
1. OT RULES & DEFINITIONS
| Question | Answer / Details | Notes
| Standard working hours per day? | TBD — e.g. 8h
| Standard working hours per week? | TBD — e.g. 40h
| Standard working hours per month? | TBD — e.g. 176h
When does OT start? (> 8h/day? > 40h/week? Both?)
Does OT require pre-approval or is it logged after the fact?
Is there a maximum OT cap? (e.g. Max 60h OT/month?)
What are the standard working hours? (9AM–6PM / flexible?)
Are there core hours? (e.g. Must be present 10AM–3PM?)
Does lunch break count towards working hours?
2. OT TYPES & MULTIPLIERS
| OT Type | When / Condition | Multiplier / Rate
| Weekday OT | Mon–Fri, after standard working hours | 1.5×
| Weekend OT — Saturday | Saturday | 2.0×
| Weekend OT — Sunday | Sunday | 2.0× or 3.0×? TBD
| Public Holiday OT | Official public holidays | 3.0×
| Night Shift OT | 10PM–6AM (if applicable) | 1.5× or 2.0×? TBD
| Compensatory Time Off | Convert OT to time off in lieu | 1:1 or 1:1.5? TBD
3. OT AUTO-DETECTION & CALCULATION
| Feature | Details / Logic | Required? (Y/N)
| Auto-detect OT | System automatically detects when > 8h logged in a day
| Auto-calculate OT hours | e.g. 10h logged = 8h regular + 2h OT
| Auto-detect OT type | Automatically identifies weekday / weekend / holiday OT
| OT approval workflow | Separate OT approval required before logging
| OT cap warning | Alert when approaching the maximum monthly OT limit
| OT report auto-send | Automatically send OT report at end of week / month
| Compensatory time tracking | Track comp-time balance earned from OT hours

## 13. Leave Management
LEAVE & TIME-OFF MANAGEMENT — REQUIREMENTS
Leave types, balances, approval workflow, and timesheet integration
1. LEAVE TYPES
| Leave Type | Details / Rules | Required? (Y/N)
| Annual Leave | Statutory paid leave — how many days per year? Carry-forward allowed?
| Sick Leave | Medical leave — is a certificate required? Maximum days?
| Unpaid Leave | Leave without pay — is there a limit?
| Maternity Leave | Per local labour law — how many days?
| Paternity Leave | Per local labour law — how many days?
| Bereavement Leave | Family bereavement — how many days?
| Marriage Leave | Wedding leave — how many days?
| Study Leave | Education leave — if applicable
| Compensatory Leave | Time off in lieu earned from OT hours
| Public Holidays | Vietnamese public holiday calendar (auto-updated) | Y
2. LEAVE BALANCE & ACCRUAL
| Question | Answer / Details | Notes
Annual leave entitlement per year? (12 days / 15 days?)
Annual leave accrual: monthly or granted at start of year?
Pro-rated annual leave for new joiners?
Carry-forward: can unused leave be carried to next year? Maximum days?
Expiry: when does leave expire? (End of year / after 6 months?)
Negative balance: can staff take leave in advance?
Leave encashment: can unused leave be converted to cash?
Half-day leave: is half-day leave supported?
3. INTEGRATION WITH TIMESHEET
| Question | Answer / Details | Notes
Do leave days automatically appear in the timesheet?
Should staff log the timesheet on leave days? (Mark as 'On Leave'?)
Do leave days count towards working hours? (e.g. Annual leave = 8h?)
Does leave affect OT calculation?
Separate Leave Management module or integrated into Timesheet?
Should leave balance be visible within the Timesheet interface?

## Template
TIMESHEET TEMPLATE — SERVICE ENTRY SHEET (Reference)
This is the current Excel template used by aTrung to send to the German team — do not modify structure
DOCUMENT HEADER
| Project | Conarum VN — SAP Development Services
| Customer | conarum GmbH & Co. KG
| Place | Germany
| Company | conarum Vietnam Company Ltd.
| Employee | Nguyen Manh Cuong
| Period | December 01, 2025
Customer Contact
ENTRY DATA — REQUIRED COLUMNS
⚙ System notes: Date auto-generated (weekends & public holidays excluded) ¦ Working Location: 'Copy All' button for bulk fill ¦ Papierkram projects: entries synced to Papierkram API
| Date | Type | Task / Description | Working Location | Hours | Project (Papierkram) | Note (Internal Projects)
| 01 Dec 2026 | Papierkram | [Meeting] Proconarum General Activity discussion |  | 2.00 | 4501725747-10-Certificate-Development-offshore
| 01 Dec 2026 | Papierkram | [Development] Worklist UI Activity |  | 6.00 | 4501725747-10-Certificate-Development-offshore
| 02 Dec 2026 | Papierkram | [Meeting] ProRequest Catch-Up Status |  | 0.50 | 4501725747-10-Certificate-Development-offshore
| 02 Dec 2026 | Papierkram | [Development] UI Activity – Filtering and Reusable Components |  | 7.50 | 4501725747-10-Certificate-Development-offshore
| 03 Dec 2026 | Papierkram | [Development] Activity UI Enhancements |  | 8.00 | 4501725747-10-Certificate-Development-offshore
| 18 Dec 2026 | Others | [Meeting] Small ball dev 2026 |  | 1.00 |  | Internal team meeting
| 18 Dec 2026 | Others | [Training] PO-POC/AB Monitor Training |  | 2.00 |  | Internal training
| ... | ... | ... |  | ... | ...
| TOTAL HOURS (December 2025) |  |  | 152.00 | 19 working days
| Signature of conarum Vietnam Employee |  |  |  | Signature of Customer Contact Person